## Sheet1
Lofthus frukt og saft |  |  | January | [19 empty] | February
Start date: 04/01/2021 - End date: 26/02/2021 |  |  | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8
Project startup |  | 10 d
Client kickoff meeting | All | 1d | 1
Research | All | 7d |  | 1 | 1 | 1 | 1 | 1 | 1
Define project scope | All | 4d |  |  |  |  | 1 | 1 | 1 | 1
Team kickoff meeting | All | 1d | [8 empty] | 1
Code and design brainstorm | C+D | 1d | [9 empty] | 1
Active development |  | 20 d
Layout design & photo | D | 3d | [10 empty] | 1 | 1 | 1
Front and backend | C | 20d | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Copywriting & content | CW | 10d | [10 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Web & UI/UX design | D | 10d | [13 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Deployment |  | 10 d
User testing | C | 5d | [30 empty] | 1 | 1 | 1 | 1 | 1
Bug fix and changes | C | 4d | [33 empty] | 1 | 1 | 1 | 1
Deployment to servers | C | 3d | [37 empty] | 1 | 1 | 1
Team Members | Group | Hours
Project Manager |  | 67.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5
Copywriter | CW | 142.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 |  | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5
Front-end developer | C | 292.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 |  | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5
Fullstack developer | C | 292.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 |  | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5
Web designer | D | 172.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5
Project total |  | 967.5